## Communication Calendar
Time of day | Activity | Activity lead | Audience | Corresponding assets | Assets lead | Assets due | Questions/Notes
Week of 7/15
TBD | Schedule post-board meeting reporter 1:1s | Kyle | Targeted reporters Stephanie Brown, WOKV Will Robinson, Jacksonville Business Journal Mike Mendenhall, JAX Daily Record | Approved list of targeted reporters | Gina | 2019-07-17 | Gina to start calling Wednesday
TBD | Upload board agenda and package to website | Bartley | General public | Board agenda & package (no powerpoints) | Bartley | 2019-07-21
TBD | Draft pension legislation | Vineyard/Lynne | City Council | Pension legislation | Sherry/Hershel | 2019-07-22
2019-07-22
3 p.m. & 4 p.m. | Internal meetings: JEA HR business partners and SLT | Zahn, Dykes & Kendrick | SLT members including VPs and HR business partners | .-Document (leave-behind): Board and SLT July board meeting messages & tough Q&A .-Documents (leave-behind): employee FAQ, generic employee letter and retention agreement OR employee severance template | Dalton Kendrick/Stewart | 2019-07-17 | Meetings have been placed on calendars
TBD | External meeting: key city council members | Zahn+ | (TH, SW, DB & AB) | .-Document: Board and SLT July board meeting messages & tough Q&A (prep-only) | Dalton | 2019-07-17
Tuesday, July 23, 2019 Board Meeting
8 a.m. | Internal meetings: union leadership | Zahn/Herschel | Union leaders | .-Document: Script (prep-only) | Dalton | 2019-07-17
8 a.m. | Internal meetings: JEA leadership (manager and above) | Dykes | JEA managers and directors | .-Document: Script (prep-only) | Dalton | 2019-07-17
9 a.m. | Calls to remaining 15 council members; notifies members of general scenarios being presented at board meeting and that JEA will get details to them following board meeting | Hall | City Council | N/A | N/A | N/A
9 a.m. | Board meeting |  | All | Board decks | TBD | 2019-07-21
1 p.m. | Distributes board materials to City Council & council auditors office | Hall | City Council & and council auditors office | .-Documents: Abbreviated board and SLT July board meeting messages; baord decks (leave-behind) |  | 2019-07-23
1 p.m. | Alan Howard to call Bobby Stein & Mike Ward | Howard | Civic Council | N/A | N/A | N/A | Aaron to ask Alan Howard
1 p.m. | Stewart to call Jeanne Miller | Stewart | Civic Council | N/A | N/A | N/A
1:30 p.m. | 1:1 media interviews (no gaggle) -- 30 minutes Targets: Stephanie Brown, WOKV Will Robinson, Jacksonville Business Journal Mike Mendenhall, JAX Daily Record | Kyle to faciliate; Zahn/Herschel spokesperson | All | .-Document: Board and SLT July board meeting messages & tough Q&A (prep-only) .-Document: Media meetings schedule (prep-only) | Dalton Kyle | 7/17/2019 7/21/19
1 p.m. | Green video | Goldberg | Employees | Teleprompter script(s) for scenario 2 & 3 | Dalton | 2019-07-18 | Location is T-16
3 p.m. (TBD) | JEA employee (non-union) letter distributed | Kendrick | Appointed employees | .-Email: Generic email to all employees with generic retention agreement and FAQ .-Hand-delivered document: Personalized retention letter; retention agreement; employee FAQ OR employee severance template | .-Letter: Goldberg .-Retention agreement: lawyers .-FAQ: Stewart/Kenrick | 2019-07-17 | Directors to hand deliver personalized employee packets
3 p.m. (TBD) | Union employee letter distributed | Kendrick | Union employees | .-Email: Generic email to all employees with generic retention agreement and FAQ .-Hand delivered document: Retention letter; retention agreement; employee FAQ OR employee severance template (Subject to collective bargaining, non-personalized) | .-Letter: Goldberg .-Retention agreement: lawyers .-FAQ: Stewart/Kenrick | 2019-07-17 | Directors to hand deliver personalized employee packets
TBD | External meetings: county leaders | Southern Strategies | Clay, Nassau & St Johns counties | .-Document: Board and SLT July board meeting messages & tough Q&A (prep-only) .-Document: Abbreviated board and SLT July board meeting messages; baord decks (leave-behind) | Pope | 2019-07-17
TBD | Talk to Duval Delegation | Hall | Duval Delegation | .-Document: Board and SLT July board meeting messages & tough Q&A (prep-only) .-Document: Abbreviated board and SLT July board meeting messages; baord decks (leave-behind) | Dalton | 2019-07-17
ONGOING
TBD ONGOING | 1:1 meetings with City Council & City Council Auditors Office | Hall/Vineyard for the first round | City Council | .-Document: Board and SLT July board meeting messages & tough Q&A | Dalton | 2019-07-17
TBD | Community leaders/non profits/civic council | TBD | Community leaders | .-Document: Board and SLT July board meeting messages & tough Q&A (prep-only) .-Document: Abbreviated board and SLT July board meeting messages; board decks (leave-behind) | Dalton | 2019-07-17
TBD | Release ITN/RFQ (Scenario 3) | SLT? | Marketplace | ITN/RFQ | TBD | TBD
August
To file Aug. 7 for the Aug. 13 council meeting | File pension legislation | Hall | City Council | Legislation language | Hall | 2019-07-17